## Sheet1
Style Vista Test Case
| Project Name | Style Vista Web Application
| Client Name | Style Vista
| Test Report by | Shubham
| Test Reported date | 2024-10-01
| Test Executed by | Pankaj
| Test Executed date | 2024-10-02
Test Case ID | Test Case Type | Test Case Description | Precondition | Steps | Expected Result | Actual Result | Status
TC-001 | Functionality Testing | Verify user registration with valid data | N/A | 1. Open the registration page https://stylevista-deployed.netlify.app/ 2. Enter valid details 3. Submit | User successfully registers | As Expected | Pass
TC-002 | Functionality Testing | Verify user receive email after registration | N/A | 1. Open the registration page 2. Enter valid details 3. Submit | User receives a confirmation email. | Not received any confirmation email | Fail
TC-003 | Functionality Testing | Test registration with existing email | User already exists | 1. Open registration page 2. Enter an already registered email 3. Submit | Error message appears: "Email already registered" | No error message is shown; instead, the user is logged in successfully. | Fail
TC-004 | Functionality Testing | Check error handling for invalid inputs | N/A | 1. Open registration page 2. Leave fields blank 3. Submit | Error message prompts users to fill in all required fields. | Error message displayed showing “Please fill out this field”. | Pass
TC-005 | Functionality Testing | Verify login with valid credentials | User is registered | 1. Open login page 2. Enter valid email and password 3. Submit | User successfully logs in and is redirected to the homepage. | User can able login successfully | Pass
TC-006 | Functionality Testing | Test login with incorrect credentials | N/A | 1. Open login page 2. Enter invalid email/password 3. Submit | Error message: "Invalid email or password" | Error message displayed: “Invalid email or password | Pass
TC-007 | Functionality Testing | Check "Remember Me" functionality | N/A | 1. Check "Remember Me" option 2. Login successfully 3. Reopen browser | User remains logged in after reopening the browser. | After revisiting the website user still logged in | Pass
TC-008 | Functionality Testing | Verify product search with valid input | N/A | 1. Open homepage 2. Enter valid product name in search bar 3. Submit | Relevant search results are displayed. | No Search bar Link not working | Fail
TC-009 | Functionality Testing | Test partial product search | N/A | 1. Open homepage 2. Enter partial product name 3. Submit | Search results related to the partial input are displayed. | No result displayed | Fail
TC-010 | Functionality Testing | Test search with invalid input | N/A | 1. Open homepage 2. Enter invalid product name 3. Submit | "No results found" message appears. | Inappropriate search bar functionality | Fail
TC-011 | Usabilti Testing | Verify filtering by category | Products exist | 1. Go to product page 2. Select a category filter 3. Apply | Products from the selected category are displayed. | As Expected | Pass
TC-012 | Usabilti Testing | Test combining multiple filters | Products exist | 1. Go to product page 2. Apply two different filters 3. Submit | Products matching both filters are displayed. | In Filter Category wise product are not displaying but price filter are working | Fail
TC-013 | Functionality Testing | Verify clearing applied filters | Products filtered | 1. Go to product page 2. Apply a filter 3. Clear the filter | All filters are cleared and all products are displayed again. | As Expected | Pass
TC-014 | Usabilti Testing | Verify product details page content | Product exists | 1. Go to product page 2. Select a product 3. Open details page | Product details (price, description, images) are displayed. | As Expected | Pass
TC-015 | UI/UX Testing | Test image zoom functionality | Product has images | 1. Go to product details page 2. Hover over product image | Image zooms in for better view | As Expected | Pass
TC-016 | Usabilti Testing | Verify out-of-stock message | Product is out of stock | 1. Go to product details page 2. Select out-of-stock product | "Out of stock" message appears | Out of stock functionality is not available. | Fail
TC-017 | Usability Testing | Verify adding product to cart | Product exists | 1. Go to product details page 2. Click "Add to Cart" | Product is added to cart, and the cart icon is updated. | Add to Cart button not adding product | Fail
TC-018 | Usability Testing | Test updating item quantity in cart | Product in cart | 1. Go to cart page 2. Change product quantity 3. Submit | Product quantity is updated, and total price is adjusted. | No quantity updation | Fail
TC-019 | Usability Testing | Verify removing product from cart | Product in cart | 1. Go to cart page 2. Click "Remove" next to product | Product is removed, and the cart updates accordingly. | Can’t be able to remove product | Fail
TC-020 | Usability Testing | Verify successful checkout process | Product in cart | 1. Go to the cart page 2. Click "Checkout" 3. Enter valid payment details | Purchase is successfully completed, and a confirmation message appears. | Checkout button not working | Fail
TC-021 | Usability Testing | Test checkout with invalid payment details | Product in cart | 1. Go to the cart page 2. Click "Checkout" 3. Enter invalid payment details | Error message appears: "Payment failed, please try again" | Payment option is not showing and checkout is not appropriate | Fail
TC-022 | Usability Testing | Verify cart is empty after successful order | Product in cart | 1. Complete checkout 2. Go back to cart page | Cart is empty after successful checkout. | Not working Properly | Fail
TC-023 | Usability Testing | Verify order status post-purchase | Order placed | 1. Log in 2. Go to "My Orders" page 3. Check order status | Order status is displayed correctly (Processing/Delivered). | No such Order functionality available | Fail
TC-024 | Usability Testing | Test order tracking with invalid order ID | N/A | 1. Go to "Track Order" page 2. Enter invalid order ID | Error message: "Order not found" | Track Order Functionality is not available | Fail
TC-025 | Usability Testing | Ensure accurate status updates | Order in different stages | 1. Place an order 2. Wait for delivery updates | Status updates reflect real-time progress (Processing, Shipped, Delivered). | Status Updation are not reflecting | Fail
TC-026 | Perfomance Testing | Verify product can be added to wishlist | User is logged in | 1. Log in 2. Go to product page 3. Click "Add to Wishlist" | Product is successfully added to the wishlist. | Wishlist Functionality is not available on this website. | Fail
TC-027 | Performance Testing | Test removing item from wishlist | Product in wishlist | 1. Go to wishlist page 2. Click "Remove" on a product | Product is removed from the wishlist. | Wishlist Functionality is not available on this website. | Fail
TC-028 | Performance Testing | Ensure logged-out users are prompted to log in before adding to wishlist | User not logged in | 1. Go to product page 2. Click "Add to Wishlist" | Prompt appears to log in before adding to the wishlist. | Wishlist Functionality is not available on this website. | Fail
TC-029 | Compatibility Testing | Verify website layout on mobile devices | Mobile browser | 1. Open website on a mobile device 2. Browse through different pages | Website layout adjusts and displays correctly on mobile. | As Expected | Pass
TC-030 | Compatibility Testing | Test desktop screen layout | Desktop browser | 1. Open website on a desktop 2. Browse through different pages | Website layout is properly responsive on desktop. | As Expected | Pass
TC-031 | Compatibility Testing | Ensure proper content display across all screen sizes | Mobile/Desktop | 1. Test on different devices (mobile, desktop) | Content and navigation work seamlessly across different screen sizes. | As Expected | Pass
TC-032 | Compatibility Testing | Verify sale prices on products. | Products marked for sale. | 1. Navigate to the sale section. 2. Select a product. 3. Check the displayed sale price vs original price. | Sale price is correctly displayed with a discount. | No price displayed with discount | Fail
TC-033 | Compatibility Testing | Ensure sale filters work properly. | Sale filters available (by category, price, etc.). | 1. Go to the sale page. 2. Apply price and category filters. | Only relevant products appear based on the selected filters. | Unwanted Product appear after applying filter | Fail
TC-034 | Functionality Testing | Verify adding sale items to the cart. | Sale products added. | 1. Select a sale product. 2. Add the product to the cart. | Sale item is added to the cart with the correct price. | Sale add to cart link is broken | Fail
TC-035 | Functionality Testing | Verify that sale products can be added to the cart with the correct | Sale product added to the cart. | 1. Add a sale product to the cart. 2. Verify the price in the cart. | Sale product is added with the sale price in the cart. | Sale add to cart link is broken | Fail
TC-036 | Functionality Testing | Verify that users can add products to the wishlist. | User is logged in. | 1. Select a product from the catalog. 2. Add the product to the wishlist. | Product is successfully added to the wishlist. | Wishslist function link is broken | Fail
TC-037 | Functionality Testing | Verify that users can remove items from the wishlist. | Product exists in the wishlist. | 1. Open the wishlist. 2. Remove a product. | Product is removed from the wishlist. | Wishslist function link is broken | Fail
TC-038 | Compatibility Testing | Ensure the wishlist is synced when logged in across multiple devices. | User is logged into multiple devices. | 1. Add a product to the wishlist on Device A. 2. Check the wishlist on Device B. | The wishlist is synced across all logged-in devices. | Wishslist function link is broken | Fail
TC-039 | Compatibility Testing | Verify that users can edit and save profile details. | User is logged in. | 1. Go to the user profile settings. 2. Edit details such as name or email. 3. Save the changes. | Profile picture is uploaded and displayed correctly. | Profile link is not working properly | Fail
TC-040 | Compatibility Testing | Verify that profile changes remain after logging out and back in. | Profile changes made. | 1. Log out. 2. Log back in. 3. Check the updated profile details. | Profile updates persist after re-login. | Profile link is not working properly | Fail
TC-041 | Functionality Testing | Verify that filtering by the "Women" category works correctly. | Products categorized under "Women" exist. | 1. Navigate to the "Women" section. 2. Verify the products displayed. | Only products under "Women" are displayed. | Category Links are not working appropriately correct | Fail
TC-042 | Functionality Testing | Verify that filtering by the "Men" category works correctly. | Products categorized under "Men" exist. | 1. Navigate to the "Men" section. 2. Verify the products displayed. | Only products under "Men" are displayed. | Category Links are not working appropriately correct | Fail
TC-043 | Functionality Testing | Verify that filtering by the "Kids" category works correctly. | Products categorized under "Kids" exist. | 1. Navigate to the "Kids" section. 2. Verify the products displayed. | Only products under "Kids" are displayed. | Category Links are not working appropriately correct | Fail
TC-044 | Performance Testing | Verify that the customer care form can be submitted. | Customer care form available. | 1. Fill out the customer care form. 2. Submit the form. | Form is submitted successfully. | No such form showing | Fail
TC-045 | Performance Testing | Verify customer care response time is within SLA. | Form submitted with a valid query. | 1. Submit a query. 2. Record response time. | Response time is within defined SLA. | Page Not found Pop-up | Fail
TC-046 | Performance Testing | Verify that users can upload attachments in the customer care form. | Customer care form has an attachment feature. | 1. Fill out the form. 2. Upload an attachment (e.g., screenshot). 3. Submit the form. | Form with attachment is submitted successfully. | Page Not found Pop-up | Fail
TC-047 | Performance Testing | Verify that a password reset email is sent when requested. | User has a valid registered email. | 1. Click on "Forgot Password." 2. Enter the registered email address. 3. Submit the request. | Password reset email is received by the user. | Forget password option is not available | Fail
TC-048 | Performance Testing | Verify that the password reset link in the email works. | Password reset email is received. | 1. Open the password reset email. 2. Click on the reset link. | Password reset page opens successfully. | Forget password option is not available | Fail
TC-049 | Performance Testing | Check if subcategories (like clothing, shoes) are working properly. | Subcategories exist under Women/Men/Kids. | 1. Select a subcategory under Women, Men, or Kids. 2. View the filtered products. | Products related to the selected subcategory are shown. | Redirected to irrelevant product page | Fail
TC-050 | Usability Testing | Ensure sale filters work properly. | Sale filters available (by category, price, etc.). | 1. Go to the sale page. 2. Apply price and category filters. | Only relevant products appear based on the selected filters. | Redirected to irrelevant product page | Fail
TC-051 | Usability Testing | Wishlist sync across devices Verify that the system handles searches with special characters correctly. | User logged in on multiple devices.Search function is available. | 1. Enter a search query with special characters (e.g., "@#$%^&*"). 2. Click on "Search." | The system either returns no results or handles special characters gracefully. | As Expected | Pass
TC-052 | Usability Testing | Verify that users can successfully apply a valid discount code. | Discount codes are available, and products are added to the cart. | 1.Add items to the cart. 2. Enter a valid discount code during checkout. 3. Click "Apply." | Discount is successfully applied, and the total amount is updated. | Discount Functionality is not available | Fail
TC-053 | Usability Testing | Verify the system’s behavior when applying an invalid discount code. | Cart is populated with items. | 1. Enter an invalid discount code during checkout. 2. Click "Apply." | An error message is displayed, stating the code is invalid. | Discount Functionality is not available | Fail
TC-054 | Usability Testing | Verify that users cannot apply multiple discount codes in a single transaction. | Valid discount codes exist, and products are added to the cart. | 1. Enter one discount code and apply it. 2. Attempt to enter a second discount code. | Only one discount code is allowed, and the second code is rejected. | Discount Functionality is not available | Fail
TC-055 | Performance Testing | Verify the system’s handling of expired discount codes. | Expired discount codes are available. | 1. Enter an expired discount code at checkout. 2. Click "Apply." | The system shows a message indicating the discount code has expired. | Discount Functionality is not available | Fail